## Sheet1
Activity | Expected Start Date | Estimate Hours (Per Person) | Actual Start date | Actual Hours spent (Per Person)
Read through of Assignment brief, and discussion. | 2018-10-22 | 2 | 18/10/2018 | 2
Create Project Plan for assignment. | 2018-10-24 | 5 | 31/10/2018 | 4
Listed all the functional requirements. | 2018-10-26 | 2 | 23/10/2018 | 5
List all attributes. | 2018-10-29 | 1 | 19/10/2018 | 1
Normalise attributes into third normal form, alongside with declaring their table name and their data types. | 2018-10-31 | 6 | 19/10/2018 | 8
Create relevant ERD for normalised data. | 2018-11-06 | 4 | 22/10/2018 | 3
Design storyboard for front-end view of system. | 2018-11-09 | 3 | 31/10/2018 | 6
Create SQL scripts to generate all tables in Oracle, alongside with constraints to relevant primary, composite and foreign keys. | 2018-11-14 | 5 | 29/10/2018 | 7
Popularised the database with relevant information. | 2018-11-23 | 4 | 26/11/2018 | 4
Create graphical user interface for front-view. | 2018-11-27 | 9 | 27/11/2018 | 15
Create Report to review Assignment. | 2018-12-07 | 9 | TBC | TBC
200
Minimum: 200